## Sheet1
Quality Assurrance Checklist
Quality Checklist
Project: Disaster Management System / Law and Order | Date: | February 14, 2017
Verfification
Quality Item | YES | NO | N/A | COMMENTS:
Does the project have an approved quality management plan? | *
Has the quality management plan been reviewed by all stakeholders? |  | *
Do all stakeholders have access to the quality management plan? |  | *
Is the quality management plan consistent with the rest of the overall project plan? | *
Have product quality metrics been established, reviewed, and agreed upon? | *
Do all metrics support a quality standard which is acceptable to the client? | *
Do all metrics have agreed upon collection mechanisms? |  |  | *
Do all metrics have an agreed upon collection frequency? |  |  | *
Have quality metrics review meetings been scheduled throughout the project's duration? | *
Are all metrics clear, measurable, controllable, and reportable? | *
Is the project team familiar with the project's quality review process? | * |  |  |  | sn
Does the project have an appropriate number of resources assigned for quality assurance and control? |  | *
Has the project team established a repository for all quality documentation? | *
Do all team members have access to the quality documentation repository? | *
Have all appropriate team members been notified of their required participation in quality reviews? | *
Have quality responsibilities been assigned and documented and the applicable personnel notified? | *
Have product and process quality standards been established, documented, and communicated? | *
Have quality thresholds and limits been established, documented, and communicated? |  |  | *
Does the change control process accommodate project changes based on quality improvements? |  |  | *
Has a project quality manager been assigned? |  |  | *
Is the project sponsor aware of his/her responsibilities relating to quality acceptance? | *
Is the customer aware of his/her responsibilities relating to quality acceptance? | *